VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

Communications between the Contracting Authority and/or the Supervisor on the one hand, and the Contractor on the other, shall be exclusively in writing. Official communications shall be sent by post or delivered by hand to the following addresses:

For the Contracting Authority:

Municipality of Yambol

Represented by Milena Mihaylova-Georgieva

Address: 8600 Yambol, 7 G.  S. Rakovsky Str.

Republic of Bulgaria

Official registration number: 000970496

For the Contractor:

……………………….

Unofficial communication will be exchanged by phone, e-mail or fax transmission.

The correspondence between the Contractor and the Contracting Authority shall be done according to the prescriptions in the Bulgarian Law of Spatial planning and all relevant Regulations.

Article 5	Supervisor and Supervisor’s representative

5.1	The power of the Supervisor and its representative is in compliance with Bulgarian legislation. The Supervisor shall be appointed under Service tender procedure applicable for the Interreg-IPA CBC Bulgaria-Turkey Programme, CCI No. 2014TC16I5CB005.

The purpose of the service contract is the provision of Independent Construction Supervisor for the implementation of the construction works required by the project in compliance with Bulgarian Law for Construction, including provisions of the Law of Spatial Planning and all other relevant Regulations.

5.2	Any approval, inspection, certificate, examination, instruction, proposal, request, test or other similar action of the Supervisor shall not relieve the Contractor of any of his duties and responsibilities under this Contract, including responsibilities for any of his mistakes, faults or discrepancies.

The Contractor must ensure that the Supervisor has free access to the construction (s) and all the documentation relevant to the implementation of the current contract and the works herein. The Supervisor shall have access to all materials or items to be installed on the sites before they are actually fixed in place.

5.4 	Instructions and/or orders issued by the Supervisor shall be by way of administrative orders. Instructions and/or orders shall be made in the compliance with Bulgarian Law on Spatial Planning in the order book of the construction.

Article 7	Subcontracting

7.1	Subcontracting is allowed. The upper limit authorised for subcontracting is 30% of the value of the tender.

- Subcontractors, suppliers and entities upon whose capacity the tenderer relies for the selection criteria must be eligible in respect of the rules on nationality and origin for the financing programme detailed in Section 9 of the Contract Notice.

Article 9	Access to the site

9.1	 The Contracting Authority shall within 15 days after commence of the Works contract give access of the Contractor to the Site in compliance with Art. 157 (1) of the Bulgarian Law of Spatial planning.

9.2	The Contracting Authority may at any time access to the site where the works are executed. The Contractor is obliged to give to representatives of the Contracting Authority,  Author supervisor, Ministry of Regional Development of the Republic in Bulgaria, JTS of the Interreg  Bulgaria – Turkey CBC Programme 2014-2020, Directorate “Management of the Funds of the EU” at MF, other EU, state, regional and local authorities, which are authorised by international agreements, Bulgarian law or other administrative act to inspect the site, free access to the site of construction, factories, workshops, etc. on the site, and generally assist them in the performance of their duties.

Article 12	General Obligations

12.9	The visibility measures must comply with rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission – http://ec.europa.eu/europeaid/work/visibility/index_en.htm_en, as well as applicable requirements of the Project Implementation Manual of Interreg-IPA Cross-border Cooperation Bulgaria-Turkey Programme.

Article 15	Performance guarantee

15.1	The performance guarantee is set to 3% of the amount of the contract.

15.8	Within 60 days after the deliverance of the certificate of provisional acceptance according to article 60.1 of the General Conditions and the completion of any outstanding work or reservation, 100 % of the amount of the performance guarantee may be released.

Article 16	Liabilities and Insurance

16.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the Contractor's liability in respect of the Contracting Authority is capped at an amount equal to the contract value.

16.1 b)	By way of derogation from Article 16.1, b), paragraph 2, of the general conditions, compensation for damage resulting from the Contractor's liability in respect of the Contracting Authority is capped at an amount equal to the contract value.

Article 17	Programme of implementation of tasks

17.1	The Contractor shall provide the Supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the Contractor proposes to carry out the works, and shall be based on the tranches foreseen in art. 49.1 of the special conditions.

17.2. 	The Supervisor shall return this document to the Contractor with any relevant remarks within 10 days of receipt, save where the Supervisor, within those 10 days, notifies the Contractor of its wish for a meeting in order to discuss the documents submitted.

Article 21	Exceptional risks

21.4	No derogation from General conditions.

Article 34	Period of implementation of tasks

34.1	Period of implementation of tasks shall be 120 days from the date of the 
work commencing on the site. Implementation will be ended with the acceptance.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 40 % of the contract price or, if the contract is subdivided into phases, 40 % of the price of the phase concerned.

Article 39	Work register

39.1    The work register is required and will be accomplished according to Art. 39 in General Conditions and as per Bulgarian legislation.

39.2	The statements shall form an integral part of the work register but may, where appropriate, be recorded in separate documents. The statements for work registration will be complied by the Contractor and will be approved by the Supervisor control at the same time.

Article 40	Origin and quality of works and materials

40.1 	All goods purchased under the Contract must originate in any eligible source country as defined in Regulation (EU) No 231/2014 of the European Parliament and of the Council of 11 March 2014 establishing an Instrument for Pre-Accession Assistance (IPA II). However, the goods to be purchased may originate from any country, whenever the total price of the estimated quantity of those goods, as reflected in a separate item of the Breakdown of the Lump-sum Price (Volume 4.2.3) is below 100.000 €. A category of similar goods to be purchased shall not be broken down over more than 1 item of the Breakdown of the Lump-sum Price (Volume 4.2.3).

When importing goods, any change in the specified origin must be pointed out to the project Supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*)	the following specifications - Technical specifications, volume 3, part of the Contract.

(*)	the requirements of Bulgarian standards and codes.

Article 43	Ownership of plant and materials

43.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the Contracting Authority

Article 44:	General principles for payments

44.1	Payments shall be made in Bulgarian national currency.

44.3	By derogation, pre-financing payment to the Contractor for the lump-sum advance shall be made within 30 days. Other pre-financing payments to the Contractor shall be made within 60 days. Interim payments to the Contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 60 days, and the final payment to the Contractor of the amounts due after the final statement of account issued by the Supervisor shall be made within 60 days.

Article 46	Pre-financing

46.1	The only prefinancing granted to the Contractor, is the lump sum advance referred to in Article 46.1(a) from General conditions.

46.2	By derogation to Article 46.2 of the General Conditions, the lump sum advance referred to in Article 46.1(a) shall be 10% of the original contract price (if requested).

46.3(c)	Pre-financing guarantee is required.

46.8	The tranches laid down in Article 49.1 of these Special Conditions are determined so that the pre-financing is fully repaid before Provisional Acceptance.

Repayment of the pre-financing shall take the form of deductions based on monthly claims. The flat-rate pre-financing (maximum of 10%) shall be repaid by means of deductions from instalments and, if necessary, the balance due to the Contractor.

This repayment shall begin with the first instalment and be completed, at the very latest, until the pre-financing is fully paid. Repayment shall be made in the same currency as the pre-financing.

The amount to be deducted from each instalment shall be 10 %.

Article 47	Retention monies

47.1	The sum retained to guarantee implementation of the Contractor’s obligations during the defects liability period is 10 % of the contract price. By derogation to Article 47.1 of the General Conditions, that money is not retained from interim payments. The tranches laid down in Article 49.1 of these Special Conditions are determined so that the retention sum amounts to 10% of the contract price at the moment of the Certificate of provisional acceptance.

47.2	By derogation to Article 47.2 of the General Conditions, the retention sums can not be substituted by a retention guarantee.

Article 48	Price revision

48.1	Prices are fixed and shall not be revised.

Article 49	Measurement

49.1	This is a lump-sum contract.

Under the conditions imposed by the Special Conditions and General Conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 10% | Lump-sum advance of Article 46.1(a) | Lump sum advance for 10% of the original contract price, after conclusion of the contract. Advance payment amounting to 10% (ten percent) of the price after submission by the CONTRACTOR of the guarantee, guaranteeing in full the funds provided in advance and a duly drawn invoice. The advance shall be deducted from subsequent interim and final payments until it is exhausted. |
| 2. | 80% | Interim payment of Article 50 | Interim payments up to 80% of the contract price, after completion of phase/percentage of quantities, cf. 49 SC. Amount of the value of the actually executed, accepted and payable construction works after approval of the payment amount and presentation of a duly drawn invoice, accompanied by the documents required by the Bulgarian legislation. From each interim payment, an advance of 10% of the completed works is deducted from the pending ones for payment. |
| … | …% | Interim payment of Article 50 | [as above] |
| .... | …% | Interim payment of Article 50 | After issuing of the Certificate of provisional acceptance |
| <last> | 10% | Retention money of Article 47 | Within 45 days of the issuing of the signed Final statement of account. Balance payment for 10% of the contract price, after completion of phase/percentage of quantities, cf. 49 SC. To the amount of the value of all actually executed and accepted and payable construction works up to the full amount of the agreed price after approval of the payment amount and signing of the Protocol for acceptance and delivery of the execution, and presentation of a duly drawn invoice, accompanied by the necessary documents according to the Bulgarian legislation. In case of a residual of the provided advance, not deducted from the interim payments, it shall be deducted from the final payment until the entire provided mind. From the final payment can be deducted amounts for accrued penalties, if any, after deduction of the advance due. |

49.2	The Contractor certifies of the Contracting Authority performed and updated works with bills of quantities, acts and protocols according to Ordinance No 3 of 2003 for the preparation of documents and reports during construction. Actual values ​​of works shall be valid for certifying the completed part of the total volume of construction works for the purpose of making interim payments.

49.3	For complete and payable construction works will be considered only those types of works that are accepted by investor’s control (if applicable) and the Consultant and are reflected in the relevant protocol.

49.4	Payments will be made in BGN, regard to the Inforeuro exchange rate leva/euro 1.95580 (http://ec.europa.eu/budget/inforeuro/index.cfm?Language=en), into the bank account of the Contractor.

Article 50	Interim payments

50.7	The interim payments will be paid as determined in Article 49.1 of these Special Conditions.

Article 61	Defects liability

  - The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.7	The warranty terms for the site are equal to the minimum specified in Ordinance No 2 of the 2003 commissioning of buildings in the Republic of Bulgaria and the minimum warranty periods for completed construction works, facilities and construction sites.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of Bulgarian Court in accordance with the national legislation of the Contracting Authority.

Article 72	Data Protection

Not applicable.

* * *